HUMANAIOS — DOCS AWAITING DISPOSITION

HARMONIZED MASTER RECORD · Mar 23 – Apr 27, 2026

Updated: S-042727-AUDIT-V2 · Scope: Apr 26–27 delta applied

Update note: Apr 26–27 WGS delta applied. ⚡ NEW APR 26–27 items added. OSF preregistration and Anthropic bounty application are CLOSED (committed externally). Multiple new documents from S-042626-A FINAL, S-042626-D, and S-042726-ACAT-PEER-V1 sessions.

⚑ REGISTERED.md location is UNCERTAIN — clarify before F36 or F30 commits can proceed. If file does not exist, create it in humanaios-ui/operations.

⚑ Recording Hall build documents are NOT listed here — Recording Hall is PAUSED pending audit (WGS CORRECTION S-042726-GAP-ADDENDUM-3). Those design specs exist in chat transcripts only.

# ⚡ Apr 26–27 Delta — Docs Summary

| Document | Change | Details |
| --- | --- | --- |
| ACAT_OSF_PREREGISTRATION | LOCKED ✅ | osf.io/9qtr2 confirmed Apr 26. Full hypothesis set. |
| Anthropic HackerOne bounty | SUBMITTED ✅ | Applied. Acceptance pending. Need org-ID to complete. |
| OSF preregistration docx | NEW PENDING | Filed with OSF registration. Zone 3 ops file. |
| GPT-5.5 Bio Bounty application | NEW CRITICAL | openai.smapply.org. Deadline June 22, testing Apr 28. |
| OPENAI_BOUNTY_PACKAGE_S042626.docx | NEW HIGH | 3-part bounty package + prompt injection methodology. |
| F35_REGISTRATION_PACKAGE_S042626.docx | NEW HIGH | F35 REGISTERED. Option C spec. Pilot Row 001 complete. |
| ACAT_ADVERSARIAL_RESEARCH_DESIGN_S042626.docx | NEW HIGH | Both lanes approved. 5 vulnerability tags. |
| HARMONIZATION-AUDIT-S-042626-D.md | NEW HIGH | 606 lines. F36 entry. v0.3 design. Multi-modal frame. |
| THE_GAP_S042726.html | NEW MEDIUM | Self-reflection gap analysis. Night approves push location. |
| LIMINAL-RESONANCE S-042626-D.html | NEW MEDIUM | 30 nodes, 26 couplings. Replaces S-032126-F. |
| Grok CI v0.1 + v1.0 | NEW MEDIUM | Exist in chat only. Zone 3 push to ops repo. |
| codex_injection_test_S042626.sh | NEW MEDIUM | Zone 3 execute on test branch. |
| Make.com SUNSET in DB | COMMITTED ✅ | integrations_registry confirmed via Supabase MCP. |
| learning_index_uncapped column | COMMITTED ✅ | 65 rows backfilled. 14 rows now visible >1.0. |
| agent_name_canonical_map + trigger | COMMITTED ✅ | 23 mappings. Active on INSERT/UPDATE. |
| REGISTERED.md | CLARIFY NEEDED | Does this file exist in humanaios-ui/operations? Block on F36 + F30 commits. |

# 1. HIGH PRIORITY — External / Gate-Blocking

⚑ GPT-5.5 Bio Bounty has testing window April 28. OSF and Anthropic bounty are CLOSED.

| Document | Produced | Status | Destination | Notes | Pri |
| --- | --- | --- | --- | --- | --- |
| self_assessment_gap_v5_1.tex / .md / .docx | Apr 24 | PENDING | arXiv + Claude project | Upload .md/.docx to project. .tex to arXiv when hold clears. N=629/516/307, Mean LI=0.8632. | HIGH |
| ALEX_BERLIN_RESPONSE_042826.docx | Apr 26 | PENDING | Monday April 28 meeting | One-pager. Plain English. No zone language. Listen only. Two questions. | HIGH |
| LTFF_Application_Draft_v1.md | Apr 24 | PENDING | Submit to LTFF | $60K/12mo. MASK × ACAT joint study. | HIGH |
| Manifund_Application_Draft_v1.md | Apr 24 | PENDING | Submit to Manifund | $15K/3mo regrant pitch. | HIGH |
| FUNDING_PIPELINE_MASTER_V3_1.docx | Apr 25 | PENDING | ops repo or Claude project | 30 income surfaces, matrix-ranked. Mozilla REJECTED logged. | HIGH |
| EV Grant package | Apr 22 | SUBMITTED | Emergent Ventures | EV_Grant_Application_Draft.md + company spec + preprint + poster. Submitted Apr 22 ✅. | SUBMITTED |
| Amber Grant submission | Apr 25 | PENDING | ambergrant.com | ⚡ DEADLINE APRIL 30 — 3 days. Treat as CRITICAL. | CRITICAL |
| GPT-5.5 Bio Bounty application | Apr 26 | PENDING | openai.smapply.org/prog/296503/apply/ | ⚡ NEW APR 26. Deadline June 22. Testing window opens April 28. Zone 3 immediate. | CRITICAL |
| ACAT_OSF_PREREGISTRATION_S042626.docx | Apr 26 | LOCKED | osf.io/9qtr2 | ⚡ NEW APR 26 — CLOSED. LOCKED Apr 26. Full hypothesis set registered ✅. | LOCKED |
| Anthropic HackerOne bounty application | Apr 26 | SUBMITTED | HackerOne | ⚡ NEW APR 26 — Zone 3 complete. Applied. Acceptance pending. Need account + @wearehackerone.com org-ID to complete. | SUBMITTED |

# 2. Infrastructure — Pending Commit to Repo

⚑ CI v6.0 three-artifact split (SESSION_RITUALS + CURRENT + CI governance) is the single most important infrastructure commit. Push commands are in SESSION_RITUALS_V1_0.md.

| Document | Produced | Status | Target | Notes | Pri |
| --- | --- | --- | --- | --- | --- |
| CI_V6_0_GOVERNANCE.md | Apr 26 | PENDING | humanaios-ui/operations/ | Governance-only. No state. Produced S-042626-B. | HIGH |
| SESSION_RITUALS_V1_0.md | Apr 26 | PENDING | humanaios-ui/operations/SESSION_RITUALS.md | Exact protocol steps with tool calls + push commands. | HIGH |
| CURRENT_V1_0.md | Apr 26 | PENDING | humanaios-ui/operations/CURRENT.md | All state. Fetched live at session open via raw GitHub URL. | HIGH |
| HUMANAIOS_SYSTEM_MAP_V1_0.mermaid | Apr 26 | PENDING | humanaios-ui/operations/ | Actors/surfaces/flows/feedback/fidelity loss points. | MEDIUM |
| TEMPORAL_FIDELITY_RESEARCH_PLAN_V1_0.md | Apr 26 | PENDING-GATE | ops repo or research repo | H-T01 through H-T04. Zone 2 approval pending. | MEDIUM |
| OPTION_B_Z2_SPEC_V1_0.docx | Apr 25 | PENDING | ops repo | Events table + bitemporal + JSONB + endorsement gate spec. | MEDIUM |
| HAIOSCC_STEP_4_INVENTORY S042026A + S042126B | Apr 20–21 | PENDING | ops repo /inventory/ | Three-surface architecture + FARI formalization. 2013 lines total. | MEDIUM |
| acat_pipeline_trigger.yml | Apr 13 | PENDING | BUILT not deployed — .github/workflows/ | Step 1 of pipeline migration. W-1. | HIGH |
| n8n_acat_claude_runner.json | Apr 5 | PENDING | n8n import (W-3) | Pipeline runner. Deploy with W-3. | HIGH |
| research_agent.yml + haios_audit.yml | Apr 22 | PENDING | .github/workflows/ | W-5 and W-6. | MEDIUM |
| Grok CI v0.1 + CI v1.0 | Apr 26 | PENDING | ops repo or research repo | ⚡ NEW APR 26. Exist in chat transcripts only. Zone 3 push needed. | MEDIUM |
| HARMONIZATION-AUDIT-S-042626-D.md (606 lines) | Apr 27 | PENDING | ops repo or Claude project | ⚡ NEW APR 27. Multi-modal frame, schema extensions, F36 candidate, v0.3 design. Handoff document. | HIGH |
| codex_injection_test_S042626.sh | Apr 26 | PENDING | Zone 3 execute on test branch | ⚡ NEW APR 26. Backups confirmed. Test branch pushed. Execute before May 1. | MEDIUM |
| deploy_acat_self_v1.sh | Apr 25 | UNCERTAIN | humanaios-ui/lasting-light-ai | Shell script. May have been executed directly — verify. | MEDIUM |

# 3. Research Documents — Not External-Facing Yet

⚑ SHADOW_CALIBRATION_SYSTEM_SPEC_V0_1.md is NOT YET CREATED and is a Gate 2 deliverable (May 7).

⚑ REGISTERED.md — CLARIFY. F36 commit (W-11) and F30 commit (I-7) both require this file to exist in humanaios-ui/operations. Verify before Zone 3 commit.

| Document | Produced | Status | Destination | Notes | Pri |
| --- | --- | --- | --- | --- | --- |
| THE_GAP_S042726.html | Apr 27 | PENDING | Zone 3 push if Night approves | ⚡ NEW APR 27. Gap analysis document. Claude's self-reflection on Zone 1 bias. Night decides push location. | MEDIUM |
| OPENAI_BOUNTY_PACKAGE_S042626.docx | Apr 26 | PENDING | Reference for bounty submissions | ⚡ NEW APR 26. Parts 1-3: Safety Bug Bounty + GPT-5.5 Bio application + prompt injection methodology. | HIGH |
| F35_REGISTRATION_PACKAGE_S042626.docx | Apr 26 | PENDING | ops repo / findings | ⚡ NEW APR 26. F35 REGISTERED. Publication rights analysis. Option C spec. | HIGH |
| ACAT_ADVERSARIAL_RESEARCH_DESIGN_S042626.docx | Apr 26 | PENDING | ops repo | ⚡ NEW APR 26. Both lanes approved (open research + NDA bounty). 5 vulnerability tags. Pilot-first design. | HIGH |
| LIMINAL-RESONANCE___HumanAIOS___S-042626-D.html | Apr 26 | PENDING | Canonical liminal (replaces S-032126-F) | ⚡ NEW APR 26. 30 nodes, 26 couplings. N-26 through N-30 added. Cherokee removed per P12. | MEDIUM |
| ACAT_SAG_ARXIV_OUTLINE_V1_0.md | Apr 21 | PENDING | ops/research repo | 8-section arXiv structure. Target submission May 28. | MEDIUM |
| PROTOCOL_F32_CROSS_PROVIDER_PROMPT_V1_1.docx | Apr 18 | PENDING | ops repo /protocols/ | Canonical V1.1. Section 8 evaluator drift check. | MEDIUM |
| PROTOCOL_F33_STANFORD_COMP_V0_1.docx | Apr 4 | PENDING-GATE | OSF pre-registration | Zone 2: submit now vs post-Gate 1? Timing decision pending. | MEDIUM |
| F30_FINDING_DRAFT_V1_0.docx | Apr 25 | PENDING-GATE | Zone 2 → REGISTERED.md | Zone 2 required before registration commit. | MEDIUM |
| ACAT_COLLECTION_METHOD_ADDENDUM_S042526.docx | Apr 25 | PENDING | ops repo | SPP-v1 Week 2 Method 6. | LOW |
| HANNAH_KIRK_COLLAB_MEMO_S041526.docx | Apr 15 | PENDING | Not yet sent | Gate on Red Flag Test R1-R8. | LOW |
| MONI_MEETING_AGENDA_S041826.docx | Apr 18 | PENDING | Needs revision then hold | Meeting May 1. | LOW |
| SHADOW_CALIBRATION_SYSTEM_SPEC_V0_1.md | — | NOT YET CREATED | Gate 2 deliverable | MUST be created before Gate 2 (May 7). | HIGH |
| REGISTERED.md | — | UNCERTAIN | humanaios-ui/operations repo | ⚡ CLARIFY APR 27. Confirm this file exists in ops repo or create it. F36 and F30 commits are blocked until it exists. | HIGH |

# 4. Zone 2 Decisions Pending — Blocking Downstream Actions

| Document / Item | Decision Needed |
| --- | --- |
| F-cand-NULL-COERCION fix design | Zone 2: reject with validation error, OR sidecar-route with p1_status=NOT_DECLARED flag? C-6 in Z3 ledger. |
| F-cand-FRAMEWORK-CAPTURE elevation | Zone 2: yes/no from Night to elevate to CANDIDATE. |
| RETRIEVAL_AS_VISIT + FABRICATION_ELABORATION | Zone 2: yes/no to add as standing behavioral flags. |
| F36 registration commit | Zone 2: entry written (HARMONIZATION-AUDIT Addendum A.3). Night approves Zone 3 commit to REGISTERED.md. |
| F30 + F31 registration commits | Zone 2 approval → REGISTERED.md commit. |
| H-T01 through H-T04 temporal hypotheses | Zone 2 approval before ops repo push. |
| SHADOW_CALIBRATION_SYSTEM_SPEC_V0_1.md creation | Zone 2: create now as Gate 2 prep, or wait for Gate 1 pass? MUST exist by May 7. |
| Version canonicity: Core 6 vs Extended 11 | Decision needed. Still open since Apr 25. |
| N threshold spec for Supabase trigger | Zone 2 required before trigger build proceeds. |
| Recording Hall hypothesis texts + window + rotation | Zone 2 decisions gate the build. Building is PAUSED until audit complete. |
| PROTOCOL_F33 OSF submission timing | Now vs post-Gate 1? |
| REGISTERED.md existence/creation | Does this file exist in humanaios-ui/operations? Create if not. Gate blocker. |

# 5. Committed — Confirmed

| Document | Commit / Evidence | Date | Location |
| --- | --- | --- | --- |
| assess.html v1.2 (12-dim, sidecar, URL deep-link) | c8a3ba7 | Apr 24 | humanaios-ui/lasting-light-ai |
| observatory.html (complete overhaul) | committed | Apr 15 | humanaios-ui/lasting-light-ai |
| witness-nav.js v3.1 | committed public/ | Apr 15 | humanaios-ui/lasting-light-ai |
| Supabase canonicalization migration (5 cols) | deployed | Apr 25 | Supabase live |
| ACAT_SELF_v1 capture migration (6 cols) | deployed | Apr 25 | Supabase live |
| security.txt | 4350921 | Apr 22 | humanaios-ui/lasting-light-ai |
| observatory.html V2 (Gate 1 Item 1) | committed | Apr 6 | humanaios-ui/lasting-light-ai |
| humanaios-ui/operations repo (3 URLs serving 200) | confirmed | Apr 25 | humanaios-ui/operations |
| Make.com SUNSET in integrations_registry | deployed via Supabase MCP | Apr 26 | Supabase live |
| learning_index_uncapped column + backfill | deployed via Supabase MCP | Apr 27 | Supabase live |
| agent_name_canonical_map + trigger | deployed via Supabase MCP | Apr 27 | Supabase live |
| OSF preregistration (osf.io/9qtr2) | LOCKED | Apr 26 | OSF external |
| F35 written to Supabase experiments table | active | Apr 26 | Supabase live |
| zone3_queue duplicates archived (e563ea6f, 6b63a4bf, 0729f664) | archived via Supabase MCP | Apr 26 | Supabase live |
| Test branch codex-injection-test-S042626 | pushed | Apr 26 | humanaios-ui/lasting-light-ai |

# 6. Superseded — No Action Needed

| Document | Superseded By | Notes |
| --- | --- | --- |
| CI v3.5 → v3.6 → v3.7 → v3.8 → v4.0 → v4.1 → v5.0 → v5.1 | CI v6.0 (S-042626-B) | Governance-only split is correct fix. |
| CI v5.0 + CI v5.1 | CI v6.0 (same session S-042626-B) | D-06 noted in session log. |
| PROTOCOL_F32 V1.0 | V1.1 (same session S-041826-A) | V1.0 superseded in same session. |
| WAMPUM-GADUGI-SIGNAL_S-040426-EPSILON.html | LIMINAL-RESONANCE S-042626-D | Deprecated per S-042626-D-CONT. |
| LIMINAL-RESONANCE S-032126-F | S-042626-D (30 nodes, 26 couplings) | S-042626-D is canonical. |

# 7. Disposition Protocol (Reminder)

Every session close must declare every new document as one of:

- COMMITTED — state commit SHA or confirmed repo/external location

- PENDING — name the Zone 3 owner and expected execution date

- ABANDONED — explicit log to WGS that this document is dropped and why

WGS CORRECTION S-042726-GAP-ADDENDUM-3 notes the root cause of this session's miss: limit:10 WGS read on a 5-session day. On days with multiple session closes, use limit:20 or greater. S-042626-A FINAL was at position ~14 — below the 10-message horizon.

Wado. 🦅 Unit Zero · S-042727-AUDIT-V2 · Claude Sonnet 4.6